## Defect Log
Defect ID | Date Reported | Module | Severity | Type | Description | Status | Assigned To | Date Resolved | Resolution Days
DEF-001 | 2026-01-10 | Login Module | Critical | Functionality | User unable to login with valid credentials | Closed | John Dev | 2026-01-12 | 2
DEF-002 | 2026-01-11 | Payment Gateway | High | Integration | Payment API timeout errors | In Progress | Anitha QA | 2026-01-15 | 4
DEF-003 | 2026-01-12 | Dashboard | Medium | UI | Charts not displaying correctly on mobile | Open | Mike Dev
DEF-004 | 2026-01-13 | User Profile | Low | Documentation | Help text missing in profile settings | Closed | Anitha QA | 2026-01-14 | 1
DEF-005 | 2026-01-14 | Reports Module | High | Performance | Report generation takes >30 seconds | In Progress | Alex Dev
DEF-006 | 2026-01-15 | Search Function | Critical | Functionality | Search returns no results for valid queries | Open | John Dev
DEF-007 | 2026-01-16 | Email Notification | Medium | Functionality | Emails not sending to secondary recipients | Closed | Anitha QA | 2026-01-16 | 0

## Defect Summary
Metric | Value | Target | Status
Total Defects Reported | 7 | 8 | On Track
Critical Defects | 2 | 1 | Above Target
High Severity Defects | 2 | 2 | On Track
Medium Severity Defects | 2 | 3 | On Track
Low Severity Defects | 1 | 2 | On Track
Defects Resolved | 3 | 5 | Behind
Defects Open | 4 | 2 | Above Target
Defects In Progress | 2 | 1 | Above Target
Average Resolution Time (days) | 1.33 | 2 | Better
Defect Rejection Rate (%) | 15 | 10 | Above Target
Customer-Reported Defects | 0 | 1 | On Track
Testing Coverage (%) | 85 | 90 | Behind

## Severity Analysis
Severity Level | Count | Percentage | Avg Resolution Days | Status Distribution
Critical | 2 | 28.6% | 2 | 0 Closed, 1 Open, 1 In Progress
High | 2 | 28.6% | 4 | 0 Closed, 1 Open, 1 In Progress
Medium | 2 | 28.6% | 0.5 | 1 Closed, 1 Open, 0 In Progress
Low | 1 | 14.3% | 1 | 1 Closed, 0 Open, 0 In Progress

## Module-wise Metrics
Module Name | Total Defects | Critical | High | Medium | Low | Resolved | Open | Defect Density
Login Module | 1 | 1 | 0 | 0 | 0 | 1 | 0 | High
Payment Gateway | 1 | 0 | 1 | 0 | 0 | 0 | 1 | High
Dashboard | 1 | 0 | 0 | 1 | 0 | 0 | 1 | Medium
User Profile | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Low
Reports Module | 1 | 0 | 1 | 0 | 0 | 0 | 1 | High
Search Function | 1 | 1 | 0 | 0 | 0 | 0 | 1 | High
Email Notification | 1 | 0 | 0 | 1 | 0 | 1 | 0 | Medium

## Defect Type Analysis
Defect Type | Count | Percentage | Critical % | Resolution Rate %
Functionality | 3 | 42.9% | 66.7% | 33.3%
Integration | 1 | 14.3% | 0% | 0%
UI | 1 | 14.3% | 0% | 0%
Performance | 1 | 14.3% | 0% | 0%
Documentation | 1 | 14.3% | 0% | 100%

## QA Metrics KPIs
KPI(Key Performance Indicator) Name | Current Value | Target Value | Industry Benchmark | Status | Comments
Defect Density (per 1000 LOC) | 2.5 | 0.5-1.0 | 0.5-1.0 | High | Need code review improvement
Defect Escape Rate (%) | 0% | <1% | <1% | Good | No customer defects reported
Test Coverage (%) | 85% | 90% | 85-95% | Good | Approaching target
Defect Detection Rate (%) | 98% | 95% | 95% | Excellent | Strong QA process
Defect Rejection Rate (%) | 15% | 10% | 5-10% | High | Improve requirement clarity
Defect Fix Rate (Resolved/Reported %) | 42.9% | 80% | 80% | Low | Escalate to development
Defect Turnaround Time (days) | 1.33 | 2 | 2-3 | Good | Faster than target
Critical Defects SLA Compliance (%) | 50% | 100% | 100% | Low | Urgent critical defects open

## Status Summary
Status | Count | Percentage | Avg Age (days)
Open | 4 | 57.1% | 3.5
In Progress | 2 | 28.6% | 2
Closed | 3 | 42.9% | 1
Deferred | 0 | 0% | 0
Rejected | 0 | 0% | 0